## Timeline
Project Name |  | Total Duration(Days) | Start Date | End Date | Submission date
Happy Pet |  | 1 month | 2021-08-23 | 2021-09-22 | 2021-09-29
Sl No. | Task Descriptions | Start Date | End Date | Duration
1 | Planning/Design
1.1 | Project Defination | 2021-08-22 | 2021-08-23 | 2 day
1.2 | Finish webpage | 2021-08-24 | 2021-08-31 | 7 days
1.3 | Project Design | 2021-08-22 | 2021-08-23 | 2 days
2 | Coding
2.1 | Phase 1 | 2021-08-24 | 2021-09-03 | 10 days
2.2 | Phase 2 | 2021-09-03 | 2021-09-10 | 10 days
2.3 | Additional Features | 2021-09-10 | 2021-09-20 | 10 days
3 | Testing
3.1 | Phase 1 Testing | 2021-08-26 | 2021-09-04 | 10 days
3.2 | Modification /Any changes | 2021-08-26 | 2021-09-04 | 10 days
3.3 | Phase 2 Testing | 2021-09-04 | 2021-09-12 | 10 days
3.4 | Modification /Any changes | 2021-09-04 | 2021-09-12 | 10 days
3.5 | Final Testing | 2021-09-13 | 2021-09-23 | 10 days
4 | Documentation
4.1 | User Guide | 2021-09-23 | 2021-09-24 | 2 day
4.2 | Presentation | 2021-09-23 | 2021-09-24 | 2 day

## Roles & Responsiblity
Roles And Responsiblities
1 | Role | Back End , Front End,Database
| Member Name | Kiran Kittur(TL)
| PRN No | 210543181043
| Description | Pet Controller,Buyer Pages(Dashboard,View pet), Seller dashboard and logic to implement the same
2 | Role | Front End,Database
| Member Name | Sayali Chavan
| PRN No | 210543181018
| Description | Database, Controller and Pages for PetCare,Trainer,Veterniary , Animal Shelter.
3 | Role | Front End,Database
| Member Name | Pranav Kolle
| PRN No | 210543181044
| Description | Home page ,CSS for all pages and Documentation.
4 | Role | Back End , Front End,Database
| Member Name | Kalpesh Desale
| PRN No | 210543181035
| Description | Database and Controller for user and pet.Pages like Registration, login,Buys display.